## Sheet1
Task_id | Task_name | start | duration | percentage | dependencies | resources
Module | Module Finalisation | 2016-01-12 | 3 | 100 |  | design
Write | Write paper | 2016-01-09 | 7 | 75 | Research | write
Cite | Create bibliography | 2016-01-12 | 12 | 60 | Research | write
Complete | Hand in paper | 2016-01-20 | 4 | 20 | Cite,Write | submit